## Slide 1: Tracking New Energy Infrastructure with Fuel Stockpiles Supplement
Data as of December 31, 2018
NETL-PUB-21856

## Slide 2: Table of Contents
Introduction
Power Plant Development Projects
  Status of Proposed U.S. New Nameplate Capacity
Electric Transmission Projects
  Status of Proposed AC Electric Transmission Projects
  Status of Proposed DC Electric Transmission Projects
Natural Gas Pipeline Projects
  Status of Proposed Natural Gas Pipeline Projects
Liquefied Natural Gas Projects
  Status of Proposed Liquefied Natural Gas Projects
Fuel Stockpiles Supplement

## Slide 3: Introduction
This report provides a perspective on energy infrastructure under development as of the end of 2018, focusing on those making significant progress toward achieving commercial operation
Project states vary from announcements to under construction
The states of “Announced” or “Early Development” are not necessarily strong indicators of commitment of major capital and human resources; development through operational capacity additions is highly dependent on the market environment
  Entry into permitting and interconnection processes nominally require some expenditure of capital by the project developer. These expenses alone are not sufficient to move a project from “Early Development” to “Advanced Development” status because there is still a high level of uncertainty, pending approvals, and alone, result in no more than project related paper.
Projects in “Advanced Development” or “Under Construction” -“Progressing Projects”- reflect a more significant financial and human resource commitment to completion and offer a better perspective of the new capacity that may be forthcoming

## Slide 4: Tracking New Power Plants and Electric Transmission Projects
This report provides a snapshot of new power plant and electric transmission activity as of December 31, 2018 based on total nameplate capacity, proposed online year (the year the project is proposed to be operational), and fuel type for power plants for the following development status categories:
Status Listing | Description
Announced | Project has been listed in an interconnection queue and has been reported publicly or has initiated a permitting action.
Early Development | Project has formally commenced the permitting process.
Advanced Development | Project meets two or more of the following criteria: financing has been secured, power purchase agreement(s) has been signed, turbine(s) has been secured, required permits have been approved, or an Engineering, Procurement, and Construction (EPC) contractor has signed on to the project. Site preparation may have begun.
Construction Begun | Project has commenced actual construction. Site preparation does not qualify, as often times a developer will engage in site preparation activities to maintain project permits.
Completed | Project has reached commercial operation.
Reported Project Status Categories and Descriptions
Source: SNL Financials and ABB Velocity Suite (2/21/2019)

## Slide 5: Tracking New Natural Gas Pipeline Projects
This report provides a current snapshot of new natural gas pipeline project activity based on proposed online year (the year the project is proposed to be operational), and capacity for the following development status categories:
Status Listing | Description
Announced | Project sponsors have publicly announced the intent to build or scope out a new pipeline.
On Hold | Project has been publicly postponed by the project sponsors, possibly indefinitely, but could be reinitiated at a later date. A project can enter this status at any point in the development process.
Pre-Filing | Project has initiated the early project development process. This step details need for facility, involved parties, regulatory agencies, existing work, and public participation plan. This step is usually initiated 7-8 months before application process.
Applied | Project has initiated the formal application with the Federal Energy Regulatory Commission (FERC). FERC prepares an Environmental Impact Statement (EIS) after conferring with concerned organizations and the public to determine necessity, safety and feasibility of a project. Regulatory approval is based upon the final EIS.
Approved | Project has received a permit to construct and operate. Usually accommodated by any conditions that must be met and market rate authority. From this point, the project must still obtain Clean Air and Water Act permits and state approval, often these permits are pursued concurrently with the FERC permit process, but are also contingent upon the EIS.
Under Construction | Project has commenced actual construction; site preparation does not qualify. Facility must file monthly reports offering a summary of activity, status of outstanding permits, current project schedule and compliance with environmental conditions outlined in the approval document.
Completed | Project has reached commercial operation.
Reported Project Status Categories and Descriptions
Source: SNL Financials and ABB Velocity Suite (2/21/2019)

## Slide 6: Tracking New Liquefied Natural Gas Projects
This report provides a current snapshot of new liquefied natural gas project activity based on proposed online year (the year the project is proposed to be operational), and capacity for the following development status categories:
Status Listing | Description
Announced | Project sponsors have publicly announced the intent to build or scope out a new facility.
Studying Feasibility | Study includes site location, marketability, need and identification of possible stakeholders. Feasibility study does not mean that the project will proceed.
On Hold | Project has been publicly postponed by the project sponsors, possibly indefinitely, but could be reinitiated at a later date. A project can enter this status at any point in the development process.
Pre-Filing | Project has initiated the early project development process. This step details need for facility, involved parties, regulatory agencies, existing work, and public participation plan. This step is usually initiated 7-8 months before application process.
Applied | Project has initiated the formal application with FERC. FERC prepares an Environmental Impact Statement (EIS) after conferring with concerned organizations and the public to determine necessity, safety and feasibility of a project. Regulatory approval is based upon the final EIS.
Approved | Project has received a permit to construct and operate. Usually accommodated by any conditions that must be met and market rate authority. From this point, the project must still obtain Section 401 permits, coastal zone clearance, Clean Air and Water Act permits, and state approval, often these permits are pursued concurrently with the FERC permit process, but are also contingent upon the EIS.
Under Construction | Project has commenced actual construction; site preparation does not qualify. Facility must file monthly reports offering a summary of activity, status of outstanding permits, current project schedule and compliance with environmental conditions outlined in the approval document.
Completed | Project has reached commercial operation.
Reported Project Status Categories and Descriptions
Source: SNL Financials and ABB Velocity Suite (2/21/19)

## Slide 7: Power Plant Development Projects
This report provides current snapshot of new power plant activity based on development status, total nameplate capacity, and proposed online year (the year the plant is proposed to be operational) for the following fuel categories:
Fuel | Description
Coal | Includes all steam based (subcritical, supercritical, ultra-supercritical, and circulated fluidized bed) and integrated gasification combined cycle units
Natural Gas (NG) | Primary gas-firing units inclusive of gas turbine (GT) (simple cycle), Combined Cycle, and Gas-Primary Steam and Internal Combustion units.
Wind | Wind turbine driven units
Nuclear | All reactor types
Solar | Includes both photovoltaic and solar thermal plants
Hydro | Includes both conventional, run-of-river, tidal, hydraulic turbine, and pumped storage units
Energy Storage | Includes battery storage, compressed air storage, flywheels, and others
Other | Includes biomass, landfill gas, municipal solid waste, geothermal, fuel cells, and others
Reported Fuel Categories and Descriptions
Source: SNL Financials and ABB Velocity Suite (2/21/2019)

## Slide 8: Tracking New Power Plants
This report provides comparisons of new power plant capacity from both the nameplate and capacity credit perspectives by fuel category using the regional capacity credit factors utilized in the NERC assessment process for wind and solar resources
  These factors are developed by the planning regions based on historical rates of peak hour performance. Regions with outlying factors are an artifact of small capacity installations or lack historical data upon which to establish a lower credit.
This report assumes interconnection level average credit for areas that do not have a specified credit
Hydroelectric resources are credited at 37% across all regions
Chart: Wind Capacity Credit (%)
| FRCC | MISO | MRO-US | NE | NY | PJM | SERC-E | SERC-N | SERC-SE | SPP | TRE-Onshore | TRE-Offshore | CAMX | NWPP | RMRG | SRSG | EASTERN IC | TEXAS IC | WESTERN IC
 | 0.156 | 0.2313 | 0.132 | 0.2 | 0.13 | 0.15 | 0.05 | 0.14 | 0.58 | 0.0786 | 0.213 | 0.213 | 0.15 | 0.12965 | 0.17629 | 0.15544
 | 0.12965 | 0.12965 | 0.12965
Chart: Solar Capacity Credit (%)
| FRCC | MISO | MRO-US | NE | NY | PJM | SERC-E | SERC-N | SERC-SE | SPP | TRE | CAMX | NWPP | RMPA | AZNMSN | EASTERN IC | TEXAS IC | WESTERN IC
Capacity Credit (%) | 0.4163 | 0.5 | 0.05 | 0.5 | 0.38 | 1 | 0.47 | 0.1 | 0.77 | 0.24 | 0.165 | 0.27 | 0.234 | 0.27251 | 0.77 | 0.206
Capacity Credit (%)2 | 0.27251 | 0.27251
Regions utilizing interconnection level credit values
Source: 2017 NERC Summer Reliability Assessment
Notes: Leave alone per John- using 2017 numbers for capacity credits

## Slide 9: Capacity Development Duration
For units entering service between 2010 and 2018, the duration from announcement to completion varied widely by technology type and fuel. Development duration is impacted by a number of factors including labor availability, component production lead times, permitting duration, market viability, etc.
Fuel | Technology Type | Development Duration (Years)
Coal | Fluidized Bed | 9.3
 | Supercritical | 9.1
 | Subcritical | 9.0
 | Integrated Gasification Combined Cycle | 10.0
Natural Gas (NG) | Combined Cycle | 6.8
 | Combustion Turbine | 4.3
 | Fuel Cell | 2.7
 | Internal Combustion | 3.4
 | Subcritical | 5.5
Petroleum | Gas Turbine | 4.7
 | Internal Combustion | 2.5
 | Fluidized Bed | 5.6
Fuel | Technology Type | Development Duration (Years)
Wind | Onshore Turbine | 4.0
 | Offshore Turbine | 8.0
Biomass | Combined Cycle | 6.0
 | Combustion Turbine | 5.2
 | Fuel Cell | 2.2
 | Internal Combustion | 2.9
 | Fluidized Bed | 6.1
 | Subcritical | 4.4
Solar | Concentrated | 6.6
 | Photovoltaic | 3.1
Hydro | Conventional | 7.0
 | Hydrokinetic | 14.1
 | Pumped Storage | 9.0
Derived from data found on: ABB Velocity Suite (2/21/2019)
Fuel | Technology Type | Development Duration (Years)
Geothermal | Binary Turbine | 5.3
Nuclear | Pressurized Water Reactor | 46.0
Energy Storage | Battery | 2.3
 | Flywheel | 1.0
* Capacity Weighted Average

## Slide 10: State of the U.S. Electric Generating Fleet
Chart: Generation Vintage
| Pre-1960s | 1960s | 1970s | 1980s | 1990s | 2000s | 2010s
Biomass (16.1) | 950.8 | 1254.7 | 965.4 | 4676.36 | 3439.58 | 1804.93 | 2969.52
Coal (261.5) | 14954.6 | 33712.6 | 108147.95 | 71716.4 | 10894.4 | 7672.7 | 14389.1
Hydro (106.7) | 35015.15 | 25507.47 | 25734.1 | 11867.21 | 5289.5 | 836.91 | 2411.91
NGCC (300.4) | 912.7 | 1373.7 | 5165.6 | 6175.2 | 29109.25 | 185530.2 | 72162.2
Non-NGCC Gas (237.9) | 13121.7 | 30026.6 | 50883.68 | 8761.37 | 23777.22 | 88008.04 | 23256.11
Nuclear (104) | 641.8 | 43350.8 | 52640.5 | 6088.6 | 1269.9
Petro (38) | 1100.47 | 4197.49 | 20906.01 | 4039.49 | 2448.81 | 3209.38 | 2093.62
Energy Storage (0.7) | 111 | 45.2 | 559.6
Solar (33) | 242 | 94.33 | 388.43 | 32262.44
Wind (97) | 16.5 | 524.22 | 1191.17 | 32796.91 | 62474.6
Other (8.1) | 722 | 363.8 | 647.4 | 3044.9 | 1397.2 | 1007.35 | 941.2
*Unlike the NERC Long-Term Reliability Assessment that considers Pumped Storage to be an Energy Storage resource, this document considers Pumped Storage to be a hydroelectric resource.
**Other consists of: Geothermal, Waste Heat, and Unclassified Gaseous Fuels
Derived from data found on: ABB Velocity Suite (2/21/2019); De-rate Factors: NERC 2017 Summer Reliability Assessment
Energy Storage is classified under the broader ‘Other’ category in this document because of the ambiguous nature of the power system and the inability to identify the source of the charging energy.
Capacity Weighted Fleet Age (Years) |  |  |  |  |  |  | 
Conventional | Coal |  |  | 40 | Renewable | Solar | 3
 | Gas |  | NGCC | 14 |  | Hydro | 53
 |  |  | Non-NGCC | 29 |  | Wind | 7
 |  |  |  |  |  | Wind | 7
 | Nuclear |  |  | 37 |  | Biomass | 28
 | Petroleum |  |  | 38 |  |  | 
Other |  | Energy Storage |  |  | 7 |  | 
 |  | Other |  |  | 30 |  | 
Notes: Updated 2/21/19
Without direct contracting for charging energy or coincident siting with a specific generating resource and the ability to verify that that resource is providing 100% of the charging energy, there are many methods for estimating the source of charging energy for energy storage resources, all of which have their flaws and merits. Rather than select one method over the other, this presentation opts to defer Energy Storage assets into a broader ‘Other’ category.
If the reader desires to perform this categorization, the author recommends using one of the following two methods: (1) Grid Generalization or (2) Marginal Resource Classification. Under the ‘Grid Generalization’ method, one would determine the composition of the generating fleet in operation during each charging period and would assign the amount of energy stored during that period to each resource type on a percentage basis, with the annual total reflecting the summation of these assignments for each charging period across the year. Under the Marginal Resource Classification method, one assumes that the energy storage resource represents the last increment of demand in each charging period, allowing the energy stored to be attributed to the marginal generating unit classification during the period, with the annual total reflecting the summation of these assignments across the year.

## Slide 11: State of the U.S. Electric Generating Fleet
Chart: Generation Vintage
| Pre-1960s | 1960s | 1970s | 1980s | 1990s | 2000s | 2010s
Biomass (16.1) | 950.8 | 1254.7 | 965.4 | 4676.36 | 3439.58 | 1804.93 | 2969.52
Coal (261.5) | 14954.6 | 33712.6 | 108147.95 | 71716.4 | 10894.4 | 7672.7 | 14389.1
Hydro (39.5) | 12955.6055 | 9437.7639 | 9521.617 | 4390.8677 | 1957.115 | 309.6567 | 892.4067
NGCC (300.4) | 912.7 | 1373.7 | 5165.6 | 6175.2 | 29109.25 | 185530.2 | 72162.2
Non-NGCC Gas (237.9) | 13121.7 | 30026.6 | 50883.68 | 8761.37 | 23777.22 | 88008.04 | 23256.11
Nuclear (104) | 641.8 | 43350.8 | 52640.5 | 6088.6 | 1269.9
Petro (38) | 1100.47 | 4197.49 | 20906.01 | 4039.49 | 2448.81 | 3209.38 | 2093.62
Energy Storage (0.1) | 110 | 0 | 1.5
Solar (12.5) | 58.08 | 22.6358 | 122.7082 | 12284.3359
Wind (12.3) | 1.2969 | 42.0489 | 151.4954 | 4628.3938 | 7431.9549
Other (8.1) | 722 | 363.8 | 647.4 | 3044.9 | 1397.2 | 1007.35 | 941.2
Capacity Weighted Fleet Age (Years) |  |  |  |  |  |  | 
Conventional | Coal |  |  | 40 | Renewable | Solar | 3
 | Gas |  | NGCC | 14 |  | Hydro | 53
 |  |  | Non-NGCC | 29 |  | Wind | 7
 |  |  |  |  |  | Wind | 7
 | Nuclear |  |  | 37 |  | Biomass | 28
 | Petroleum |  |  | 38 |  |  | 
Other |  | Energy Storage |  |  | 7 |  | 
 |  | Other |  |  | 30 |  | 
*Unlike the NERC Long-Term Reliability Assessment that considers Pumped Storage to be an Energy Storage resource, this document considers Pumped Storage to be a hydroelectric resource.
**Other consists of: Geothermal, Waste Heat, and Unclassified Gaseous Fuels
Derived from data found on: ABB Velocity Suite (2/21/2019); De-rate Factors: NERC 2017 Summer Reliability Assessment
Energy Storage is classified under the broader ‘Other’ category in this document because of the ambiguous nature of the power system and the inability to identify the source of the charging energy.
Notes: Updated 2/21/19
Without direct contracting for charging energy or coincident siting with a specific generating resource and the ability to verify that that resource is providing 100% of the charging energy, there are many methods for estimating the source of charging energy for energy storage resources, all of which have their flaws and merits. Rather than select one method over the other, this presentation opts to defer Energy Storage assets into a broader ‘Other’ category.
If the reader desires to perform this categorization, the author recommends using one of the following two methods: (1) Grid Generalization or (2) Marginal Resource Classification. Under the ‘Grid Generalization’ method, one would determine the composition of the generating fleet in operation during each charging period and would assign the amount of energy stored during that period to each resource type on a percentage basis, with the annual total reflecting the summation of these assignments for each charging period across the year. Under the Marginal Resource Classification method, one assumes that the energy storage resource represents the last increment of demand in each charging period, allowing the energy stored to be attributed to the marginal generating unit classification during the period, with the annual total reflecting the summation of these assignments across the year.

## Slide 12: State of the U.S. Electric Generating Fleet
Chart: Retirement Year
| 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Biomass (2.2) | 188.1 | 95.8 | 109.3 | 169.52 | 171.5 | 325.3 | 394 | 208 | 378.3 | 103.5 | 66 | 23
Coal (101) | 1832.7 | 3101.6 | 10101 | 6393.5 | 4850.8 | 16668 | 8826.1 | 6453.6 | 14788.9 | 7477.5 | 4351.9 | 2165.8 | 5846.3 | 2160.8 | 598.4 | 3656.8 | 1238.3 | 550
Hydro (1.7) | 138.83 | 172.8 | 285 | 216.1 | 189.3 | 118.9 | 114.6 | 115.6 | 46 | 12 | 243.9 | 50
NGCC (5.9) | 136.5 | 219.5 | 141.6 | 466.3 | 853.1 | 1260.4 | 319.5 | 1165.5 | 379.9 | 537.3 | 120.5 | 290
Non-NGCC Gas (55.3) | 5733 | 3031.3 | 3272.2 | 5286.5 | 2586.8 | 6698.5 | 6797.4 | 6273.6 | 6013.8 | 3041.1 | 4814.7 | 200 | 325 | 817 | 326.4 | 78.8
Nuclear (13.9) | 3704.5 | 563.4 | 502 | 550 | 670 | 1299 | 1012 | 811.8 | 1159 | 1164 | 2449.9
Petro (14.3) | 2161.7 | 1797.1 | 2162.7 | 1768.6 | 1896 | 1404 | 1311.3 | 851.2 | 465.68 | 213.6 | 25.3 | 44.5 | 223.5
Energy Storage (0) | 13 | 4.5 | 2 | 20
Solar (0) | 1 | 2 | 1.5 | 3 | 8.3 | 44.4 | 3.4
Wind (1.2) | 2.2 | 37 | 14.2 | 10.8 | 127.5 | 545.06 | 131.9 | 55.86 | 39.8 | 194.7
Other (0.6) | 45 | 65.3 | 123.6 | 20 | 67.3 | 141.4 | 62 | 110 | 5.4
Coal, Natural Gas, Wind, Nuclear, Solar, Hydro*, Energy Storage, & Other**
Derived from data found on: ABB Velocity Suite (2/21/2019)
Notes: Updated 2/21/19 – only updated 2018 and beyond.

## Slide 13: Proposed U.S. New Nameplate Capacity
Chart: Proposed Online Year
| 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
Coal (0.02) | 17
Hydro (0.7) | 46.3 | 266.02 | 25 | 118.57 | 72.2 | 137.2 | 6.3 | 9.6
NGCC (59.6) | 8289.7 | 7044.8 | 19619.7 | 15948.73 | 3606 | 2125 | 2100 | 916
Non-NGCC Gas (11.5) | 2874.48 | 2974 | 2343.42 | 1042.3 | 241 | 1314 | 723
Nuclear (10.7) | 1117 | 1117 | 2520 | 480 | 1040 | 1100 | 1100 | 1100 | 1100
Solar (40.1) | 10157.77 | 16609.54 | 7858.19 | 1442.39 | 980 | 860 | 510 | 510 | 580 | 230 | 250 | 120
Wind (81.5) | 19793.19 | 37364.8 | 8525.4 | 3891.55 | 4288.4 | 1693.5 | 4765 | 750 | 400
Energy Storage (11.4) | 251.35 | 1009.5 | 184.5 | 849 | 185 | 1200 | 3873.3 | 1200 | 1316 | 1300
Other (3.7) | 546.8 | 590.2 | 2266.9 | 329.9 | 3.2
Coal, Natural Gas, Wind, Nuclear, Solar, Hydro, Energy Storage, & Other*
Derived from data found on: S&P Global (2/21/19)
*Other consists of: Petroleum, Biomass, Geothermal, Waste Heat, and Unclassified Gaseous Fuels; Pumped Hydro and Compressed Air Energy Storage are counted under the Energy Storage category;
Non-NGCC Gas includes all other gas firing technologies, including gas turbines and reciprocating engines
Notes: Updated 2/21/19
2020 Wind number higher than last year spreadsheet. 2017 deck showed 19 GW for 2018, current data shows only 7 built. Also, 2019 number is slightly lower than last year’s deck.
NG = Natural gas - Gas Turbines and Combined Cycle
done

## Slide 14: Proposed U.S. New Creditable Capacity
Chart: Proposed Online Year
| 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
Coal (0.02) | 17
Hydro (0.2) | 17.131 | 98.4274 | 9.25 | 43.8709 | 26.714 | 50.764 | 2.331 | 3.552
NGCC (59.6) | 8289.7 | 7044.8 | 19619.7 | 15948.73 | 3606 | 2125 | 2100 | 916
Non-NGCC Gas (11.5) | 2874.48 | 2974 | 2343.42 | 1042.3 | 241 | 1314 | 723
Nuclear (10.7) | 1117 | 1117 | 2520 | 480 | 1040 | 1100 | 1100 | 1100 | 1100
Solar (17.6) | 4531.0421 | 7974.773 | 3517.923 | 696.04 | 243.87 | 176.4 | 92.4 | 92.4 | 109.2 | 55.2 | 60 | 28.8
Wind (11.5) | 2508.6534 | 5144.0182 | 1351.1043 | 647.9395 | 718.7682 | 304.5858 | 580.129 | 159.75 | 80
Energy Storage (11.4) | 251.35 | 1009.5 | 184.5 | 849 | 185 | 1200 | 3873.3 | 1200 | 1316 | 1300
Other (3.7) | 546.8 | 590.2 | 2266.9 | 329.9 | 3.2
Coal, Natural Gas, Wind, Nuclear, Solar, Hydro, Energy Storage, & Other*
Derived from data found on: S&P Global (2/21/19); De-rate Factors: NERC 2017 Summer Reliability Assessment
*Other consists of: Petroleum, Biomass, Geothermal, Waste Heat, and Unclassified Gaseous Fuels; Pumped Hydro and Compressed Air Energy Storage are counted under the Energy Storage category;
Non-NGCC Gas includes all other gas firing technologies, including gas turbines and reciprocating engines
Notes: Updated 2/21/19
NG = Natural gas - Gas Turbines and Combined Cycle
done

## Slide 15: Current Capacity Projects
Fuel Category |  | Number of Units | Nameplate Capacity (MW) | Creditable Capacity (MW)
Coal |  | 1 | 17 | 17
Natural Gas | Combined Cycle | 182 | 59,650 | 59,650
 | Combustion Turbine | 71 | 10,525 | 10,525
 | Internal Combustion | 85 | 906 | 906
 | Other | 9 | 81 | 81
Nuclear |  | 21 | 10,674 | 10,674
Conventional SUB TOTAL |  | 369 | 81,853 | 81,853
Solar |  | 675 | 40,108 | 17,578
Wind |  | 386 | 81,472 | 11,495
Hydro |  | 122 | 681 | 252
Renewable SUB TOTAL |  | 1,183 | 122,261 | 29,325
Mechanical Storage |  | 27 | 10,005 | 10,005
Electro-chemical Storage |  | 38 | 1,364 | 1,364
Storage SUB TOTAL |  | 65 | 11,369 | 11,369
Other |  | 59 | 3,737 | 3,737
Other SUB TOTAL |  | 59 | 3,737 | 3,737
TOTAL |  | 1,676 | 219,220 | 126,284
Units proposed for entry into service after January 1, 2019
Non-Renewable Projects
Renewable Projects
*Other consists of: Biomass, Geothermal, Waste Heat, Petroleum, and Unclassified Gaseous Fuels.
Derived from data found on: S& P Global (2/21/19); De-rate Factors: NERC 2017 Summer Reliability Assessment
Energy Storage Projects
Notes: 15
Updated 2/21/19

## Slide 16: Status of Proposed U.S. New Nameplate Capacity
Chart: Proposed Online Year
| Coal | NGCC | Non-NGCC Gas | Other | Water | Solar | Wind | Energy Storage | NGCC | Non-NGCC Gas | Other | Water | Solar | Wind | Energy Storage | NGCC | Non-NGCC Gas | Nuclear | Other | Water | Solar | Wind | Energy Storage | NGCC | Non-NGCC Gas | Nuclear | Other | Water | Solar | Wind | Energy Storage | NGCC | Non-NGCC Gas | Water | Solar | Wind | Energy Storage | NGCC | Non-NGCC Gas | Nuclear | Other | Water | Solar | Wind | Energy Storage | NGCC | Non-NGCC Gas | Water | Solar | Wind | Energy Storage | Nuclear | Solar | Wind | Energy Storage | NGCC | Nuclear | Water | Solar | Wind | Nuclear | Solar | Energy Storage | Solar | Nuclear | Solar | Energy Storage | Nuclear | Nuclear |  | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | '29 | 2030 | '31 | '32
Completed (6.4) | 3403.1 | 366.48 | 13.3 | 6 | 1184.02 | 1325.33 | 71.8
Construction Begun (29.9) | 17 | 3561.7 | 1246.7 | 238.4 | 31 | 2863.72 | 7024.3 | 24.8 | 5765.8 | 488 | 2 | 192.68 | 224.5 | 1518.7 | 2600 | 1117 | 96 | 180 | 1146 | 1117 | 400
Advanced Development (39.7) | 335.9 | 22.7 | 118.1 | 2.3 | 1124.75 | 2076.14 | 11.75 | 964 | 941 | 90.2 | 3.2 | 1978.38 | 5816.15 | 100 | 6017 | 484 | 2149.9 | 25 | 945 | 1423.6 | 5367.3 | 63.3 | 27.89 | 84.99 | 1660 | 724 | 1416 | 72.2 | 1344.4 | 2520 | 320 | 6.3 | 480 | 750 | 240
Early Development (118) | 989 | 1151.6 | 145 | 7 | 4660.83 | 8491.92 | 134 | 315 | 1481 | 419.2 | 54.64 | 13270.06 | 22876.7 | 909.5 | 10752.7 | 1053.42 | 21 | 6084.7 | 4566 | 129.5 | 9435.43 | 979 | 329.9 | 90.68 | 1355.87 | 2231.55 | 125 | 1100 | 241 | 980 | 2384 | 160 | 625 | 914 | 137.2 | 860 | 1373.5 | 1200 | 2100 | 723 | 510 | 4000 | 393.3 | 510 | 800 | 580 | 1100 | 230 | 250 | 1100 | 120 | 1300 | 1100 | 1100
Announced (25.3) | 87 | 32 | 324.45 | 875.5 | 9 | 64 | 78.8 | 15.5 | 1136.6 | 7153.25 | 250 | 806 | 828.49 | 2355.8 | 55 | 1.53 | 1090 | 560 | 25 | 1500 | 3.2 | 765 | 3480 | 1200 | 916 | 9.6 | 400 | 1316
219.2 GW in Total
Derived from data found on: S&P Global (2/21/19)
Coal, Natural Gas, Wind, Nuclear, Solar, Hydro, Energy Storage, Other*
*Other consists of: Biomass, Geothermal, and other Unclassified Fuels
Notes: Updated 2/21/19

## Slide 17: Status of Proposed U.S. New Creditable Capacity
Chart: Proposed Online Year
| Coal | NGCC | Non-NGCC Gas | Other | Water | Solar | Wind | Storage | NGCC | Non-NGCC Gas | Other | Water | Solar | Wind | Storage | NGCC | Non-NGCC Gas | Nuclear | Other | Water | Solar | Wind | Storage | NGCC | Non-NGCC Gas | Nuclear | Other | Water | Solar | Wind | Storage | NGCC | Non-NGCC Gas | Water | Solar | Wind | Storage | NGCC | Non-NGCC Gas | Nuclear | Other | Water | Solar | Wind | Storage | NGCC | Non-NGCC Gas | Water | Solar | Wind | Storage | Nuclear | Solar | Wind | Storage | NGCC | Nuclear | Water | Solar | Wind | Nuclear | Solar | Storage | Solar | Nuclear | Solar | Storage | Nuclear | Nuclear |  | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | '29 | 2030 | '31 | '32
Completed (4.4) | 3403.1 | 366.48 | 13.3 | 2.22 | 407.8053 | 181.3151 | 71.8
Construction Begun (20.4) | 17 | 3561.7 | 1246.7 | 238.4 | 11.47 | 1330.8708 | 846.0401 | 24.8 | 5765.8 | 488 | 2 | 71.2916 | 65.1394 | 221.652 | 2600 | 1117 | 96 | 27 | 1146 | 1117 | 400
Advanced Development (26.4) | 335.9 | 22.7 | 118.1 | 0.851 | 654.1068 | 250.5204 | 11.75 | 964 | 941 | 90.2 | 1.184 | 788.8494 | 956.1334 | 100 | 6017 | 484 | 2149.9 | 9.25 | 521.465 | 282.2859 | 5367.3 | 63.3 | 10.3193 | 84.99 | 321.18 | 724 | 1416 | 26.714 | 253.9572 | 2520 | 68.16 | 2.331 | 480 | 159.75 | 240
Early Development (61.3) | 989 | 1151.6 | 145 | 2.59 | 2016.0997 | 1106.5495 | 134 | 315 | 1481 | 419.2 | 20.2168 | 6609.2223 | 3172.1341 | 909.5 | 10752.7 | 1053.42 | 21 | 2375.073 | 746.7936 | 129.5 | 9435.43 | 979 | 329.9 | 33.5516 | 610.285 | 326.7595 | 125 | 1100 | 241 | 243.87 | 353.595 | 160 | 625 | 914 | 50.764 | 176.4 | 236.4258 | 1200 | 2100 | 723 | 92.4 | 520 | 393.3 | 92.4 | 800 | 109.2 | 1100 | 55.2 | 60 | 1100 | 28.8 | 1300 | 1100 | 1100
Announced (13.6) | 87 | 32 | 122.1595 | 124.2283 | 9 | 64 | 78.8 | 5.735 | 511.562 | 794.0987 | 250 | 806 | 621.385 | 295.0248 | 55 | 0.765 | 1090 | 111.216 | 25 | 1500 | 3.2 | 60.129 | 3480 | 1200 | 916 | 3.552 | 80 | 1316
126.3 GW in total
Derived from data found on : S& P Global (2/21/19); De-rate Factors: NERC 2017 Summer Reliability Assessment
Coal, Natural Gas, Wind, Nuclear, Solar, Hydro, Energy Storage, Other*
*Other consists of: Biomass, Geothermal, and other Unclassified Fuels
Notes: Updated 2/21/19
NG = Natural gas - Gas Turbines and Combined Cycle
done

## Slide 18: Current Uncertain Capacity Projects
General Status |  | Announced |  |  | Early Development |  | 
 |  | Number of Plants | Nameplate Capacity (MW) | Creditable Capacity (MW) | Number Of Plants | Nameplate Capacity (MW) | Creditable Capacity (MW)
Coal |  | — | — | — | — | — | —
Natural Gas | Combined Cycle | 6 | 3,756 | 3,756 | 68 | 25,317 | 25,317
 | Combustion Turbine | 4 | 935 | 935 | 39 | 6,337 | 6,337
 | Internal Combustion | 5 | 22 | 22 | 32 | 206 | 206
 | Other | — | — | — | — | — | —
Nuclear |  | — | — | — | 5 | 5,200 | 5,200
Conventional SUB TOTAL |  | 15 | 4,713 | 4,713 | 144 | 37,060 | 37,060
Solar |  | 29 | 2,291 | 1,256 | 371 | 29,411 | 12,469
Wind |  | 41 | 12,110 | 1,465 | 212 | 45,924 | 6,462
Hydro |  | 5 | 25 | 9 | 42 | 290 | 107
Renewable SUB TOTAL |  | 75 | 14,426 | 2,730 | 625 | 75,625 | 19,038
Mechanical Storage |  | 8 | 6,021 | 6,021 | 16 | 3,260 | 3,260
Electro-chemical Storage |  | 3 | 64 | 64 | 22 | 1,091 | 1,091
Storage SUB TOTAL |  | 11 | 6,085 | 6,085 | 38 | 4,351 | 4,351
Other |  | 7 | 114 | 114 | 20 | 915 | 915
Other SUB TOTAL |  | 7 | 114 | 114 | 20 | 915 | 915
Uncertain SUB TOTAL |  | 108 | 25,338 | 13,642 | 814 | 117,150 | 60,563
Units proposed for entry into service after January 1, 2019
*Other consists of: Biomass, Petroleum, Geothermal, Waste Heat, and Unclassified Gaseous Fuels.
Derived from data found on: S&P Global (2/21/19); De-rate Factors: NERC 2017 Summer Reliability Assessment
Notes: 18
Updated 2/21/19

## Slide 19: Current Progressing Capacity Projects
General Status |  | Advanced Development |  |  | Construction Begun |  |  | Completed |  | 
 |  | Number of Plants | Nameplate Capacity (MW) | Creditable Capacity (MW) | Number Of Plants | Nameplate Capacity (MW) | Creditable Capacity (MW) | Number Of Plants | Nameplate Capacity (MW) | Creditable Capacity (MW)
Coal |  | — | — | — | 1 | 17 | 17 | — | — | —
Natural Gas | Combined Cycle | 44 | 14,100 | 14,100 | 55 | 13,074 | 13,074 | 9 | 3,403 | 3,403
 | Combustion Turbine | 8 | 1,299 | 1,299 | 18 | 1,849 | 1,849 | 2 | 106 | 106
 | Internal Combustion | 9 | 149 | 149 | 25 | 273 | 273 | 14 | 256 | 256
 | Other | 1 | 63 | 63 | 4 | 13 | 13 | 4 | 5 | 5
Nuclear |  | 14 | 3,240 | 3,240 | 2 | 2,234 | 2,234 | — | — | —
Conventional SUB TOTAL |  | 76 | 18,851 | 18,851 | 105 | 17,460 | 17,460 | 29 | 3,770 | 3,770
Solar |  | 113 | 4,133 | 2,049 | 100 | 3,088 | 1,396 | 62 | 1,184 | 408
Wind |  | 78 | 13,390 | 2,292 | 44 | 8,723 | 1,095 | 11 | 1,325 | 181
Hydro |  | 59 | 137 | 51 | 15 | 224 | 83 | 1 | 6 | 2
Renewable SUB TOTAL |  | 250 | 17,660 | 4,392 | 159 | 12,035 | 2,574 | 74 | 2,515 | 591
Mechanical Storage |  | 3 | 724 | 724 | — | — | — | — | — | —
Electro-chemical Storage |  | 3 | 112 | 112 | 5 | 25 | 25 | 5 | 72 | 72
Storage SUB TOTAL |  | 6 | 836 | 836 | 5 | 25 | 25 | 5 | 72 | 72
Other |  | 13 | 2,358 | 2,358 | 16 | 336 | 336 | 3 | 13 | 13
Other SUB TOTAL |  | 13 | 2,358 | 2,358 | 16 | 336 | 336 | 3 | 13 | 13
Likely SUB TOTAL |  | 345 | 39,705 | 26,437 | 285 | 29,856 | 20,395 | 111 | 6,370 | 4,446
Units proposed for entry into service after January 1, 2019
*Other consists of: Biomass, Petroleum, Geothermal, Waste Heat, and Unclassified Gaseous Fuels
Derived from data found on: S&P Global (2/21/19); De-rate Factors: NERC 2017 Summer Reliability Assessment
Notes: 19
Updated 2/21/19

## Slide 20: Electric Transmission Projects*
Many generator interconnections often require the parallel development of transmission infrastructure to achieve operation and grid interconnection. These projects often have their own timelines and can lead to delays in generator operation.
If a significant amount of the uncertain capacity fails to develop, the need for additional transmission infrastructure to deliver output from existing capacity and to maintain reliability may arise.
Similar to generation, transmission project development duration is impacted by a number of factors including labor availability, component production lead times, permitting duration, market viability, etc.
Typical Project Timeline for New Transmission
24 – 36 Months
Planning & Engineering
12 – 18 Months
Environmental Studies
24 – 36 Months
Permits & Approvals
24 – 36 Months
Construction
7 – 10.5 Years
*Bulk Electric System Only
Source: Edison International, Getting to Know Renewable Energy (2012) http://inside.edison.com/content/inside/2012/08-12/gtk-8-12.html
Notes: Link no longer exists.

## Slide 21: Status of Proposed AC Electric Transmission Projects*
Chart: Proposed Online Year & Voltage Level
| 115 | 120 | 138 | 161 | 230 | 345 | 500 | 69 | 115 | 138 | 161 | 230 | 345 | 500 | 765 | 70 | 115 | 138 | 161 | 220 | 230 | 345 | 362 | 500 | 115 | 138 | 230 | 345 | 500 | 525 | 230 | 345 | 500 | 230 | 500 | 230 | 500 | 500 | 230 | 500 | 2019 | 2020 | 2021 | 2022 | 2023 | '24 | '25 | '26 | '27
Announced | 87 | 140 | 87 | 76 | 18 | 125 | 41 | 45 | 80 | 97.1 | 56 | 13 | 151 | 64 | 16 | 46 | 124 | 140 | 26 | 60 | 123 | 30
Early Development | 56 | 27 | 113 | 98 | 37 | 223 | 26.8 | 206 | 373 | 320 | 2940 | 12 | 27 | 120 | 211 | 33 | 94 | 17 | 271 | 97 | 11 | 121 | 361 | 213 | 100 | 297 | 24 | 71
Advanced Development | 81 | 39 | 16 | 86 | 24 | 132 | 253 | 406 | 1039 | 7 | 66 | 21 | 82 | 225 | 675 | 22 | 30 | 62 | 422
Construction Begun | 15 | 195 | 351 | 839 | 33 | 59 | 56 | 38 | 168 | 357 | 139 | 30 | 107
Derived from data found on: S&P Global (2/21/19)
*17,594 AC miles in total, Bulk Electric System Only
Notes: Updated 2/21/19

## Slide 22: Current AC Electric Transmission Projects*
General Status | Sub-100 kV |  | 115 kV |  | 120 kV |  | 138 kV |  | 161 kV | 
 | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage
Completed | ― | ― | ― | ― | ― | ― | ― | ― | ― | ―
Construction Begun | ― | ― | 5 | 74.0 | ― | ― | 10 | 251.0 | ― | ―
Certain SUB TOTAL | ― | ― | 5 | 74.0 | ― | ― | 10 | 251.0 | ― | ―
Advanced Development | 1 | 7.0 | 4 | 90.0 | ― | ― | 12 | 234.0 | 1 | 39.0
Postponed | ― | ― | ― | ― | ― | ― | ― | ― | ― | ―
Early Development | ― | ― | 12 | 384.0 | 2 | 27.0 | 8 | 156.8 | ― | ―
Announced | 1 | 18.0 | 8 | 200.1 | ― | ― | 18 | 367.0 | 4 | 141.0
Uncertain SUB TOTAL | 2 | 25.0 | 24 | 674.1 | 2 | 27.0 | 38 | 757.8 | 5 | 180.0
TOTAL | 2 | 25.0 | 29.0 | 748.1 | 2.0 | 27.0 | 48.0 | 1,008.8 | 5.0 | 180.0
Uncertain Projects
*Bulk Electric System Only
Derived from data found on: S&P Global (2/21/19)
Certain Projects
Notes: 22
Updated 2/21/19

## Slide 23: Current AC Electric Transmission Projects*
General Status | 220 kV |  | 230 kV |  | 345 kV |  | 500 kV |  | 765 kV | 
 | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage
Completed | ― | ― | ― | ― | ― | ― | ― | ― | ― | ―
Construction Begun | 6 | 139.0 | 7 | 419.0 | 12 | 1,114.0 | 2 | 390.0 | ― | ―
Certain SUB TOTAL | 6 | 139.0 | 7 | 419.0 | 12 | 1,114.0 | 2 | 390.0 | ― | ―
Advanced Development | ― | ― | 15 | 373.0 | 12 | 747.0 | 13 | 2,198.0 | ― | ―
Postponed | ― | ― | ― | ― | ― | ― | ― | ― | ― | ―
Early Development | 1 | 27.0 | 22 | 716.0 | 25 | 1,286.0 | 9 | 962.0 | 15 | 2,940.0
Announced | ― | ― | 17 | 519.0 | 3 | 220.0 | 5 | 180.0 | ― | ―
Uncertain SUB TOTAL | 1 | 27.0 | 54 | 1,608.0 | 40 | 2,253.0 | 27 | 3,340.0 | 15 | 2,940.0
TOTAL | 7 | 166.0 | 61 | 2,027.0 | 52 | 3,367.0 | 29 | 3,730.0 | 15 | 2,940.0
Uncertain Projects
*Bulk Electric System Only
Derived from data found on: S&P Global (2/21/19)
Certain Projects
Notes: 23
Updated 2/21/19

## Slide 24: Status of Proposed DC Electric Transmission Projects*
Chart: Proposed Online Year & Voltage Level
| 345 | 320 | 450 | 600 | 200 | 345 | 500 | 320 | 345 | 400 | 230 | 320 | 500 | 600 | 525 | 2019 | 2020 | 2021 | 2022 | 2023 | 2025
Announced | 23 | 349
Early Development | 125 | 79 | 60 | 766 | 315 | 59 | 59 | 265 | 850
Advanced Development | 207 | 700 | 400 | 485 | 73 | 1505
Construction Begun
Completed
Postponed
*6,320 DC miles in total, Bulk Electric System Only
Derived from data found on: S&P Global (2/21/19)
Notes: Updated 2/21/19
NG = Natural gas - Gas Turbines and Combined Cycle

## Slide 25: Current DC Electric Transmission Projects*
General Status | 200 kV |  | 230 kV |  | 320 kV |  | 345 kV |  | 400 kV | 
 | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage
Completed | ― | ― | ― | ― | ― | ― | ― | ― | ― | ―
Construction Begun | ― | ― | ― | ― | ― | ― | ― | ― | ― | ―
Certain SUB TOTAL | ― | ― | ― | ― | ― | ― | ― | ― | ― | ―
Advanced Development | ― | ― | ― | ― | 5 | 765.0 | ― | ― | ― | ―
Postponed | ― | ― | ― | ― | ― | ― | ― | ― | ― | ―
Early Development | 1 | 79.0 | 1 | 59.0 | 4 | 1,031.0 | 2 | 375.0 | 1 | 59.0
Announced | ― | ― | ― | ― | ― | ― | 1 | 23.0 | ― | ―
Uncertain SUB TOTAL | 1 | 79.0 | 1 | 59.0 | 9 | 1,796.0 | 3 | 398.0 | 1 | 59.0
TOTAL | 1 | 79.0 | 1 | 59.0 | 9 | 1,796.0 | 3 | 398.0 | 1 | 59.0
Uncertain Projects
*Bulk Electric System Only
Derived from data found on: S&P Global (2/21/19)
Certain Projects
Notes: 25
Updated 2/21/19

## Slide 26: Current DC Electric Transmission Projects*
General Status | 450 kV |  | 500 kV |  | 525 kV |  | 600 kV | 
 | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage | Number of Projects | Mileage
Completed | ― | ― | ― | ― | ― | ― | ― | ―
Construction Begun | ― | ― | ― | ― | ― | ― | ― | ―
Certain SUB TOTAL | ― | ― | ― | ― | ― | ― | ― | ―
Advanced Development | ― | ― | 1 | 400.0 | ― | ― | 3 | 2,205.0
Postponed | ― | ― | ― | ― | ― | ― | ― | ―
Early Development | 1 | 125.0 | 1 | 850.0 | ― | ― | ― | ―
Announced | ― | ― | ― | ― | 1 | 349.0 | ― | ―
Uncertain SUB TOTAL | 1 | 125.0 | 2 | 1,250.0 | 1 | 349.0 | 3 | 2,205.0
TOTAL | 1 | 125.0 | 2 | 1,250.0 | 1 | 349.0 | 3 | 2,205.0
Uncertain Projects
*Bulk Electric System Only
Derived from data found on: S&P Global (2/21/19)
Certain Projects
Notes: 26
Updated 2/21/19

## Slide 27: Natural Gas Pipeline Projects
Given the expected buildout of new natural gas power generation, the time required to develop natural gas pipeline infrastructure should also be considered in parallel to capacity and transmission development in estimating when a unit will achieve operation and grid interconnection.
Unlike other fuel infrastructures that are demand responsive, the source-to-sink nature of the natural gas system and costs involved in pipeline construction trigger advance utilization planning and contracts prior to development.
Typical Transmission Project Timeline for New Transmission
Typical Project Timeline for New Interstate Pipeline
Source: FERC timeline: Traditional vs. Pre-filing. [Online] n.d. [Cited: November 19, 2014]. Adapted from http://www.fs.fed.us/specialuses/documents/im2003-197attach3.pdf.

## Slide 28: Status of Proposed Natural Gas Pipeline Projects
Chart: Proposed Online Year & Type
| Compressor Station | Expansion/Interconnect | Interstate Expansion | Interstate Replacement | New Intrastate | Lateral | New Interstate | Compressor Station | Export | Interstate Expansion | Interstate Replacement | New Intrastate | Export | Interstate Expansion | Export | Interstate Expansion | New Intrastate | New Interstate | 2019 | 2020 | 2021 | 2022
Announced | 5954 | 10200 | 2054
Studying Feasibility | 2054
Applied | 400 | 350 | 1900 | 600 | 6470 | 596.375 | 275 | 1970 | 2000 | 2000
Approved | 157.5 | 65 | 106.66
Under Construction | 483.5 | 190 | 1440 | 206.66 | 2500
Operational | 300 | 600
*5,448 miles/42.9 Bcf in total
Derived from data found on: ABB Velocity Suite (2/21/2019)
Notes: Updated 3/15/19
NG = Natural gas - Gas Turbines and Combined Cycle

## Slide 29: Current Natural Gas Pipeline Projects
Certain Projects
General Status | Compressor Station |  |  | Expansion/Interconnect |  |  | Export |  | 
 | Number of Projects | Mileage | Capacity Added (MMcf) | Number of Projects | Mileage | Capacity Added (MMcf) | Number of Projects | Mileage | Capacity Added (MMcf)
Completed | ― | ― | ― | 1 | 0.0 | 300.0 | ― | ― | ―
Under Construction | ― | ― | ― | 2 | 0.5 | 483.5 | ― | ― | ―
Approved | 2 | 0 | 222.5 | ― | ― | ― | ― | ― | ―
Certain SUB TOTAL | 2 | 0 | 222.5 | 3 | 0.5 | 783.5 | ― | ― | ―
Applied | ― | ― | ― | ― | ― | ― | 4 | 190.8 | 10,440.0
Pre-Filing | ― | ― | ― | ― | ― | ― | ― | ― | ―
Feasibility Study | ― | ― | ― | ― | ― | ― | ― | ― | ―
Announced | ― | ― | ― | ― | ― | ― | ― | ― | ―
On Hold | ― | ― | ― | ― | ― | ― | ― | ― | ―
Uncertain SUB TOTAL | ― | ― | ― | ― | ― | ― | 4 | 190.8 | 10,440.0
TOTAL | 2 | 0 | 222.5 | 3 | 0.5 | 783.5 | 4 | 190.8 | 10,440.0
Uncertain Projects
Derived from data found on: ABB Velocity Suite (2/21/2019)
Notes: 29
Updated 3/15/19

## Slide 30: Current Natural Gas Pipeline Projects
Certain Projects
General Status | Lateral |  |  | New Interstate |  |  | New Intrastate |  | 
 | Number of Projects | Mileage | Capacity Added (MMcf) | Number of Projects | Mileage | Capacity Added (MMcf) | Number of Projects | Mileage | Capacity Added (MMcf)
Completed | ― | ― | ― | ― | ― | ― | ― | ― | ―
Under Construction | ― | ― | ― | 1 | 199.4 | 1,440.0 | ― | ― | ―
Approved | ― | ― | ― | ― | ― | ― | ― | ― | ―
Certain SUB TOTAL | ― | ― | ― | 1 | 199.4 | 1,440.0 | ― | ― | ―
Applied | 1 | 42.7 | 1,900.0 | 2 | 201.0 | 2,600.0 | ― | ― | ―
Pre-Filing | ― | ― | ― | ― | ― | ― | ― | ― | ―
Feasibility Study | ― | ― | ― | ― | ― | ― | 1 | 470.0 | 2,054.0
Announced | ― | ― | ― | ― | ― | ― | 9 | 4,044.0 | 18,208.0
On Hold | ― | ― | ― | ― | ― | ― | ― | ― | ―
Uncertain SUB TOTAL | 1 | 42.7 | 1,900.0 | 2 | 201.0 | 2,600.0 | 10 | 4,514.0 | 20,262.0
TOTAL | 1 | 42.7 | 1,900.0 | 3 | 400.4 | 4,040.0 | 10 | 4,514.0 | 20,262.0
Uncertain Projects
Derived from data found on: ABB Velocity Suite (2/21/2019)
Notes: 30
Updated 3/15/19

## Slide 31: Current Natural Gas Pipeline Projects
Certain Projects
General Status | Interstate Expansion |  |  | Replacement/Upgrades |  | 
 | Number of Projects | Mileage | Capacity Added (MMcf) | Number of Projects | Mileage | Capacity Added (MMcf)
Completed | 1 | 0.0 | 600.0 | ― | ― | ―
Under Construction | 3 | 14.2 | 2,896.7 | ― | ― | ―
Approved | 1 | 12.8 | 106.7 | ― | ― | ―
Certain SUB TOTAL | 5 | 27.0 | 3,603.3 | ― | ― | ―
Applied | 3 | 117.9 | 996.4 | 2 | 154.6 | 625
Pre-Filing | ― | ― | ― | ― | ― | ―
Feasibility Study | ― | ― | ― | ― | ― | ―
Announced | ― | ― | ― | ― | ― | ―
On Hold | ― | ― | ― | ― | ― | ―
Uncertain SUB TOTAL | 3 | 117.9 | 996.4 | 2 | 154.6 | 625
TOTAL | 8 | 144.9 | 4,599.7 | 2 | 154.6 | 625
Uncertain Projects
Derived from data found on: ABB Velocity Suite (2/21/2019)
Notes: 31
Updated 3/15/19

## Slide 32: Liquefied Natural Gas Projects
In the age of abundant natural gas, many entities have decided to pursue construction of liquefied natural gas (LNG) export facilities. The volumes of gas utilized by these facilities represent a major domestic end use source and price driver.
Unlike other fuel projects that are domestic use only, LNG terminals trigger advance consideration of international markets, utilization planning, and contracts prior to development.
Typical Transmission Project Timeline for New Transmission
Typical Project Timeline for New Liquefied Natural Gas Terminal
Source: FERC timeline: Traditional vs. Pre-filing. [Online] n.d. [Cited: November 19, 2014].
Adapted from http://www.fs.fed.us/specialuses/documents/im2003-197attach3.pdf.

## Slide 33: Status of Proposed Liquefied Natural Gas Projects
Chart: Proposed Online Year & Type
| Export Terminal | Export Terminal | Offshore Export Terminal | Auxilary Peaking Facility | Export Terminal | Export Terminal | Export Terminal | Export Terminal | 2019 | 2020 | 2021 | 2022 | 2023 | 2024
Announced | 0.001
Pre-Filing | 1.788 | 2.001 | 1.2
Applied | 1.409 | 4.134 | 1.6 | 0.8 | 3.468 | 4.468 | 1
Approved | 1.2 | 0.68
Under Construction | 2.001
*25.75 Bcf/d in total
Derived from data found on: ABB Velocity Suite (2/21/2019)
Notes: Updated 3/15/19
NG = Natural gas - Gas Turbines and Combined Cycle

## Slide 34: Fuel Stockpiles Supplement
Unlike natural gas and some other liquid fuels that are utilized by the power sector, a large quantity of coal is continually maintained in on-site stockpiles at coal-fired power generators to ensure reliability and continued plant operation
While natural gas is used for power, natural gas storage is primarily leveraged by pipeline operators and local distribution companies (LDCs) to ensure reliable pipeline pressures and to meet a regulated LDC utility’s obligation to serve
Petroleum product stockpiles are primarily used for market balancing

## Slide 35: After an early year peak, utility coal stockpiles returned to near decadal average
Chart: Implied Average Coal Stockpiles by Origin (Days of Burn)
Derived from: ABB Velocity Suite Monthly Plant Estimated Coal Stockpile & Monthly Plant Coal Transactions & Costs Intelligent Queries through December 2017 (2/21/2019)
*Other US: Southern Appalachia, West/Northwest, and Central Interior
*Imports: Australia, Indonesia, Venezuela, Columbia, Russia, Canada, and Others

## Slide 36: After an early year peak, utility coal stockpiles returned to near decadal average
Chart: Implied Utility Coal Stockpiles (DoB)
Chart: Implied Utility Coal Stockpiles (DoB)
Chart: Implied Utility Coal Stockpiles (DoB)
Chart: Implied Utility Coal Stockpiles (DoB)
Derived from: ABB Velocity Suite Monthly Plant Estimated Coal Stockpile & Monthly Plant Coal Transactions & Costs Intelligent Queries through December 2017 (2/21/2019)

## Slide 37: After an early year peak, utility coal stockpiles returned to near decadal average
Chart: Implied Utility Coal Stockpiles (DoB)
Chart: Implied Utility Coal Stockpiles (DoB)
Chart: Implied Utility Coal Stockpiles (DoB)
Chart: Implied Utility Coal Stockpiles (DoB)
Derived from: ABB Velocity Suite Monthly Plant Estimated Coal Stockpile & Monthly Plant Coal Transactions & Costs Intelligent Queries through December 2017 (2/21/2019)

## Slide 38: Natural gas storage levels are near their lowest point this decade
Source: EIA Weekly Natural Gas Storage Report through December 2017, http://ir.eia.gov/ngs/ngs.html (2/21/19)
Chart: Estimated Natural Gas Storage (Bcf)
Notes: Verified 3/15/19

## Slide 39: U.S. petroleum stockpiles have fallen by more than 30% since the start of the decade
Chart: U.S. Petroleum Product Stockpiles (MMBBl)
Source: ABB Velocity Suite State Monthly Fuel Stockpile Intelligent Queries through December 2017 (2/21/2019)

## Slide 40: Petroleum coke stockpiles have become essentially non-existent compared to the beginning of the decade
Chart: U.S. Petroleum Coke Stockpiles (ktons)
Source: ABB Velocity Suite State Monthly Fuel Stockpile Intelligent Queries through December 2017 (2/21/2019)

## Slide 41
Questions/Comments Contact:
John Brewer
Systems Engineering and Analysis Directorate
Energy Markets Analysis Team
John.Brewer@netl.doe.gov
(304) 285 – 4858