## CMR Template
NATIONAL ENERGY TECHNOLOGY LABORATORY
COST MANAGEMENT REPORT
1 Title: | Project Research Support Services (PRSS) | [12 empty] | 2 Reporting Period: |  | 12/1/2012 to 12/31/2012 |  |  |  | 3 Identification Number: |  | DE-FE000400X Mod # 001
4 Participant Name and Address: | MY COMPANY, LLC | [12 empty] | 5 Cost Plan Date: |  | 11/16/2009 to 09/30/2013 |  |  |  | 6 Contract Start Date: |  | 2009-11-16
| 4567 Apple Lane, Anywhere, USA | [18 empty] | 7 Contract Completion Date: |  | 2014-11-30
Element Identification | [9 empty] | Obligations |  | Plan |  | Accrued Costs | [5 empty] | Projections
8 CLIN/SubCLIN/Task/Activity Number / Title | 9 Rev | 10 Fund Code | 11 Approp Year | 12 Reporting Entity | 13 Object Class Code | 14 Program Number | 15 Project No | 16 WFO | 17 Local Use | 18 Current FY Obligations | 19 Total Obligations | 20 Approved FY Cost Plan | 21 Total Plan Value | Reporting Period |  | FY to date |  | Cumulative to Date
[14 empty] | 22 Actual | 23 Plan | 24 Actual | 25 FY Balance of Plan | 26 Actual | 27 Plan | 28 Open Commitments | 29 Next Month Plan | 30 FY Total Cost | 31 Funds Fully Costed Date
000400X.200.01 - Project Research Support for the Natural Gas & Oil Program
000400X.200.01 | Orig | 00150 | 2010 | 220211 | 25100 | 1610260 | 0000000 | 0000000 | 0000000 | 75000 | 75000 | 90114.1667 | 109935.8333 | 7651.7677 | 8349.1667 | 9023.2218 | 76972.9167 | 11396.7677 | 13141.25 | 625.05 | 7779.1667 | 86620.4167
000400X.200.01 | Orig | 00150 | 2010 | 220211 | 25100 | 1610261 | 0000000 | 0000000 | 0000000 | 50000 | 50000 | 60076.1111 | 73290.5556 | 5101.1785 | 5566.1111 | 6015.4812 | 51315.2778 | 7597.8451 | 8760.8333 | 416.7 | 5186.1111 | 57746.9444
000400X.200.01 | Orig | 00150 | 2010 | 220211 | 25100 | 1610262 | 0000000 | 0000000 | 0000000 | 55000 | 55000 | 66083.7222 | 80619.6111 | 5611.2963 | 6122.7222 | 6615.297 | 56446.8056 | 8357.6297 | 9636.9167 | 458.25 | 5704.7222 | 63521.6389
TASK TOTAL | [9 empty] | 180000 | 180000 | 216274 | 263846 | 18364.2425 | 20038 | 21654 | 184735 | 27352.2425 | 31539 | 1500 | 18670 | 207889 | 2013-09-01
000400X.300.01.01 - Project Research Support - Base Program (North)
000400X.300.01.01 | B | 00150 | 2009 | 220318 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 5800 | 0 | 5800 | 0 | 0 | 0 | 0 | 5800 | 5800 | 0 | 0 | 0
000400X.300.01.01 | B | 00150 | 2010 | 220318 | 25100 | 1610232 | 0000000 | 0000000 | 0000000 | 100000 | 891159 | 173037 | 893189 | 20886.63 | 15033 | 202180 | 27979 | 836633 | 840395 | 11487 | 12946 | 187282
ACTIVITY TOTAL | [9 empty] | 100000 | 896959 | 173037 | 898989 | 20886.63 | 15033 | 202180 | 27979 | 842433 | 846195 | 11487 | 12946 | 187282 | 2013-04-01
000400X.300.01.02 - Project Research Support - Base Program (South)
000400X.300.01.02 | A | 00150 | 2009 | 220620 | 25100 | 1610314 | 0000000 | 0000000 | 0280023 | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458
ACTIVITY TOTAL | [9 empty] | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458 | 2013-01-01
000400X.300.01.03 - Project Research Support - Base Program (West)
000400X.300.01.03 - Project Research Support - Base Program (West) | B | 00150 | 2010 | 220140 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 345570 | 204500.3126 | 422614.4999 | 0 | 0 | 71237.25 | 0 | 343723 | 349930 | 0 | 0 | 71237.25
000400X.300.01.03 - Project Research Support - Base Program (West) | B | 05200 | 2011 | 220112 | 25100 | 1610920 | 0000000 | 0000000 | 0000000 | 24910 | 24910 | 14741.1604 | 30463.6606 | 0 | 0 | 24687.99 | 0 | 24687.99 | 25224 | 0 | 0 | 24687.99
000400X.300.01.03 - Project Research Support - Base Program (West) | B | 00197 | 2012 | 220112 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 104956 | 104956 | 62110.527 | 128355.8395 | 22008.07 | 23446 | 55401.82 | 211014 | 55401.82 | 65128 | 3257 | 23446 | 173075 | 2013-02-01
ACTIVITY TOTAL | [9 empty] | 129866 | 475436 | 281352 | 581434 | 22008.07 | 23446 | 151327.06 | 211014 | 423812.81 | 440282 | 3257 | 23446 | 269000.24 | 2013-01-01
000400X.300.01.00 - Project Management Support - Base Program
TASK TOTAL | [9 empty] | 249589 | 1392118 | 482837 | 1518527 | 47251.73 | 43643 | 358083.06 | 249370 | 1270821.81 | 1304547 | 23797 | 86682 | 477740.24
000400X.500.02.00 - ARRA - Project Research Support
000400X.500.02.00 | A | 05794 | 2009 | 220520 | 25100 | 1005098 | 2004040 | 0000000 | 0000000 | 1121 | 1121 | 1617 | 2166 | 247.64 | 293 | 260 | 590 | 260 | 1027 | 515 | 286 | 1220
TASK TOTAL | [9 empty] | 1121 | 1121 | 1617 | 2166 | 247.64 | 293 | 260 | 590 | 260 | 1027 | 515 | 286 | 1220 | 2013-02-01
32 Total | [9 empty] | 430710 | 1573239 | 700728 | 1784539 | 65863.6125 | 63974 | 379997.06 | 434695 | 1298434.0525 | 1337113 | 25812 | 105638 | 686849.24
33 Figures Expressed In: Whole Dollars | [9 empty] | 34 Signature of Participant's Project Manager and Date | [5 empty] | 35 Signature of Participant's Authorized Financial Representative and Date
36 NOTES:

## Invoice Detail
NATIONAL ENERGY TECHNOLOGY LABORATORY
INVOICE/STAFFING DATA
1 Participant Name and Address |  |  | 4 Invoice No.: 0002
MY COMPANY, LLC |  |  | 5 Invoice Date: May 14, 2015
4567 Apple Lane |  |  | 6 Billing Period: April 1 - 30, 2015
Anywhere, WV 26505
2 Contract No.: DE-FE000400X
3 CLIN/SubCLIN/Task/Activity No. and Title: 0400X.200.01 - Project Management Support for the Natural Gas & Oil Program
[5 empty] | Current Period | [8 empty] | Cumulative
7 Name | 8 Labor Category (E N/E) or Description | 9 Status | 10 Employer | 11 Current Rate | 12 Hours Worked of Available | 13 Total Cost Current Period | 14 Total FTE Hours | 15 Labor by Site | [5 empty] | 16 Hours | 17 Prev Costs | 18 Current Cost
[8 empty] | Mgn | Pgh | Alb | Sugar Land | AK | Offsite
160
Pines, Barbara | Program Manager (E) | FT | MCL | 110 | 8 | 880 | 0.05 | 0.05 | [5 empty] | 12 | 440 | 1320
Little, Douglas | Senior Management Analyst (E) | FT | MCL | 95 | 16 | 1520 | 0.1 | 0.1 | [5 empty] | 24 | 760 | 2280
McGuire, Steve | Junior Management Analyst (E) | FT | MCL | 75 | 24 | 1800 | 0.15 |  | 0.15 |  |  |  |  | 36 | 900 | 2700
Walker, John | Engineer/Scientist 5 (E) | FT | JFC | 70 | 80 | 5600 | 0.5 | 0.25 | 0.25 |  |  |  |  | 120 | 2800 | 8400
Hope, Nadine | Business/Engineer Anlyst 3 (E) | FT | JFC | 64 | 64 | 4096 | 0.4 | [5 empty] | 0.4 | 96 | 2048 | 6144
Ford, Wade | Data Entry Operator 3 (N/E) | FT | MCL | 22.5 | 24 | 540 | 0.15 | [5 empty] | 0.15 | 36 | 270 | 810
| 19 DIRECT LABOR SUB-TOTAL: |  |  |  | 216 | 14436 | 1.35 | 0.4 | 0.4 | 0 | 0 | 0 | 0.55 | 324 | 7218 | 21654
| 20 LABOR G&A | 1.57% |  |  |  | 226.6452
| 21 TOTAL DIRECT LABOR |  |  |  |  | 14662.6452
|  | PLAN | ACTUAL
22 (Planned/Actual Labor hours - Current) |  | 216 | 216
23 (Planned/Actual Labor hours - Cumulative) |  | 324 | 318
24 Other Direct Costs (ODCs) | 25 Description
26 Subcontracts | BRD Consulting, Inc. |  |  |  |  | 340.5 | [8 empty] | 0 | 340.5
27 Materials | Office Supplies |  |  |  |  | 780 | [8 empty] | 500 | 1280
28 Travel | Steve McGuire |  |  |  |  | 1000 | [8 empty] | 0 | 1000
29 Training | PMI, Inc. |  |  |  |  | 1500 | [8 empty] | 1000 | 2500
30 Total ODCs | [5 empty] | 3620.5 | [8 empty] | 1500 | 5120.5
31 G&A |  | 8.5% |  |  |  | 307.7425 | [8 empty] | 270 | 577.7425
32 Fee | [5 empty] | 0 | [8 empty] | 0 | 0
33 Total Cost & Fee | [5 empty] | 18364.2425 | [8 empty] | 8988 | 27352.2425

## Staffing Report Summary
NATIONAL ENERGY TECHNOLOGY LABORATORY
Staffing Report Summary
Cost Reimbursable FTE /Headcount Data
1 Participant Name and Address: |  |  |  | 2 Contract No.: |  | DE-FE0099999
CEMENT 64 , LLC
4567 Apple Lane |  |  |  | 3 Reporting Period: |  | April 1 - 30, 2015
Myra, WV 25544
11 FTE Staffing by NETL Location
4 Task/Activity | 5 Program Number | 6 Project Number | 7 WFO | 8 Local Use | 9 Reporting Entity | 10 Reporting Period Cost | Mgn | Pgh | Alb | Sugar Land | AK | Offsite | TOTAL
0
0
0
0
0
0
0
0
0
0
0
TOTAL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 Headcount Staffing Summary
|  |  |  | MGN |  | 0
|  |  |  | PGH |  | 0
|  |  |  | ALB |  | 0
|  |  |  | Sugar Land |  | 0
|  |  |  | AK |  | 0
|  |  |  | Offsite |  | 0
|  |  |  | TOTAL |  | 0

## OC Detail Report
OPEN COMMITMENT DETAIL REPORT
FOR PERIOD ENDING: MARCH 31, 2015
CLIN/TASK/ACTIVITY | DEFERRALS | AWARD FEE PERIOD X | AWARD FEE PERIOD XX | RATE ADJUSTMENT RESERVE | SUBCONTRACT | OTHER 1 | TOTAL OC
0023456.100.01.02 | 2000 | 6000 | 1000.5 | 48000 | 1500 | 150 | 58650.5
0023456.100.01.03 | 1500 | 6000 | 1000 | 25000 | 0 | 0 | 33500
0023456.100.01.04 | 1200 | 6000 | 1000 | 20000 | 2000 | 0 | 30200
0023456.100.01.05 | 0 | 6000 | 1000 | 15000 | 1000 | 0 | 23000
0023456.100.01.06 | 500 | 6000 | 1000 | 10000 | 500 | 0 | 18000
0023456.200.02.01 | 0 | 6000 | 1000 | 5000 | 1000 | 0 | 13000
0023456.200.02.02 | 0 | 6000 | 1000 | 1000 | 500 | 0 | 8500
TOTAL | 5200 | 42000 | 7000.5 | 124000 | 6500 | 150 | 184850.5
NOTES:
1 - Severance pay for Dona