## CMR Template
NATIONAL ENERGY TECHNOLOGY LABORATORY
COST MANAGEMENT REPORT
1 Title: | Mission Support Services (MSS) | [12 empty] | 2 Reporting Period: |  | 1/1/2024 to 1/31/2024 |  |  |  | 3 Identification Number: |  | 89243323CFE000099 Mod # 004
4 Participant Name and Address: | MY COMPANY, LLC | [12 empty] | 5 Cost Plan Date: |  | 6/1/2023 to 5/31/2026 |  |  |  | 6 Contract Start Date: |  | 2023-06-01
| 4567 Apple Lane, Anywhere, USA 30789 | [18 empty] | 7 Contract Completion Date: |  | 2026-05-31
Element Identification | [9 empty] | Obligations |  | Plan |  | Accrued Costs | [5 empty] | Projections
8 CLIN/SubCLIN/Task/ Activity Number / Title | 9 Rev | 10 Fund Code | 11 Approp Year | 12 Reporting Entity | 13 Object Class Code | 14 Program Number | 15 Project No | 16 WFO | 17 Local Use | 18 Current FY Obligations | 19 Total Obligations | 20 Approved FY Cost Plan | 21 Total Plan Value | Reporting Period |  | FY to date |  | Cumulative to Date
[14 empty] | 22 Actual | 23 Plan | 24 Actual | 25 FY Bal of Plan | 26 Actual | 27 Plan | 28 Open Commitments | 29 Next Month Plan | 30 FY Total Cost | 31 Funds Fully Costed Date
23CFE000099.01.001.000 - Strategic and Technical Outreach Support
23CFE000099.01.001.000 | Orig | 05450 | 2020 | 220318 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 5800 | 0 | 5800 | 0 | 0 | 0 | 0 | 5800 | 5800 | 0 | 0 | 0
23CFE000099.01.001.000 | Orig | 00150 | 2023 | 220318 | 25100 | 1610232 | 0000000 | 0000000 | 0000000 | 100000 | 891159 | 173037 | 893189 | 20886.63 | 15033 | 202180 | 27979 | 836633 | 840395 | 11487 | 12946 | 187282
SUBCLIN TOTAL | [9 empty] | 100000 | 896959 | 173037 | 898989 | 20886.63 | 15033 | 202180 | 27979 | 842433 | 846195 | 11487 | 12946 | 187282 | 2024-04-01
23CFE000099.01.002.000 - Education and Outreach Support
23CFE000099.01.002.000 | Orig | 00150 | 2022 | 220620 | 25100 | 1610314 | 0000000 | 0000000 | 0280023 | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458
SUBCLIN TOTAL | [9 empty] | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458 | 2024-03-01
23CFE000099.01.003.000 - General Logistical Support
23CFE000099.01.003.000 | Orig | 00150 | 2022 | 220140 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 345570 | 204500.3126 | 422614.4999 | 0 | 0 | 71237.25 | 0 | 343723 | 349930 | 0 | 0 | 71237.25
23CFE000099.01.003.000 | Orig | 05200 | 2022 | 220112 | 25100 | 1610920 | 0000000 | 0000000 | 0000000 | 24910 | 24910 | 14741.1604 | 30463.6606 | 0 | 0 | 24687.99 | 0 | 24687.99 | 25224 | 0 | 0 | 24687.99
23CFE000099.01.003.000 | Orig | 00190 | 2023 | 220112 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 104956 | 104956 | 62110.527 | 128355.8395 | 22008.07 | 23446 | 55401.82 | 211014 | 55401.82 | 65128 | 3257 | 23446 | 173075 | 2024-02-01
SUBCLIN TOTAL | [9 empty] | 129866 | 475436 | 281352 | 581434 | 22008.07 | 23446 | 151327.06 | 211014 | 423812.81 | 440282 | 3257 | 23446 | 269000.24 | 2024-05-01
23CFE000099.01.004.000 - GES Capability Support
23CFE000099.01.004.000 | Orig | 00150 | 2022 | 220318 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 5800 | 0 | 5800 | 0 | 0 | 0 | 0 | 5800 | 5800 | 0 | 0 | 0
23CFE000099.01.004.000 | Orig | 00150 | 2022 | 220318 | 25100 | 1610232 | 0000000 | 0000000 | 0000000 | 100000 | 891159 | 173037 | 893189 | 20886.63 | 15033 | 202180 | 27979 | 836633 | 840395 | 11487 | 12946 | 187282
SUBCLIN TOTAL | [9 empty] | 100000 | 896959 | 173037 | 898989 | 20886.63 | 15033 | 202180 | 27979 | 842433 | 846195 | 11487 | 12946 | 187282 | 2024-04-01
23CFE000099.01.000.000 - Logistical and Product Support
CLIN 1 TOTAL | [9 empty] | 349589 | 2289077 | 655874 | 2417516 | 68138.36 | 58676 | 560263.06 | 277349 | 2113254.81 | 2150742 | 35284 | 99628 | 665022.24
23CFE000099.02.001.001 - Computational Design and Simulation For Extreme Environment Materials
23CFE000099.02.001.001 | Orig | 00150 | 2021 | 232300 | 25104 | 1611079 | 1022406 | 0000000 | 0281805 | 32630 | 32630 | 8559.0773 | 35334.1637 | 3333.505 | 935.7522 | 3333.505 | 7623.3251 | 3333.505 | 935.7522 | 37.82 | 929.6759 | 8201.98 |  | 31%
23CFE000099.02.001.001 | Orig | 00150 | 2022 | 232300 | 25104 | 1611079 | 1022406 | 0000000 | 0281905 | 72450 | 72450 | 19050.8495 | 78647.0096 | 0 | 2082.8032 | 3333.505 | 16968.0463 | 3333.505 | 2082.8032 | 84.18 | 2069.2785 | 18256.02 |  | 69%
TASK TOTAL | [9 empty] | 105080 | 105080 | 27609.9268 | 113981.1733 | 3333.505 | 3018.5554 | 6667.0099 | 24591.3714 | 6667.0099 | 3018.5554 | 122 | 2998.9544 | 26458 | 2024-10-14
23CFE000099.02.001.002 - Materials Data Analytics
23CFE000099.02.001.002 | B | 00150 | 2022 | 220140 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 345570 | 204500.3126 | 422614.4999 | 0 | 0 | 71237.25 | 0 | 343723 | 349930 | 0 | 0 | 71237.25
23CFE000099.02.001.002 | B | 05200 | 2022 | 220112 | 25100 | 1610920 | 0000000 | 0000000 | 0000000 | 24910 | 24910 | 14741.1604 | 30463.6606 | 0 | 0 | 24687.99 | 0 | 24687.99 | 25224 | 0 | 0 | 24687.99
23CFE000099.02.001.002 | B | 00190 | 2023 | 220112 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 104956 | 104956 | 62110.527 | 128355.8395 | 22008.07 | 7487.5185 | 55401.82 | 211014 | 55401.82 | 65128 | 3257 | 23446 | 173075 | 2024-02-01
TASK TOTAL | [9 empty] | 129866 | 475436 | 281352 | 581434 | 22008.07 | 7487.5185 | 151327.06 | 211014 | 423812.81 | 440282 | 3257 | 23446 | 269000.24 | 2024-04-01
23CFE000099.02.001.003 - Simulation of the Manufacture of Large Scale Ingots of Advanced Heat-Resistant Alloys for FE Applications
23CFE000099.02.001.003 | Orig | 00150 | 2022 | 220620 | 25100 | 1610314 | 0000000 | 0000000 | 0280023 | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458
TASK TOTAL | [9 empty] | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458 | 2024-03-01
23CFE000099.02.001.004 - CPJ7 and 650C 9-12% Cr Martensitic-Ferritic Steel Development
23CFE000099.02.001.004 | Orig | 00150 | 2022 | 220140 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 345570 | 204500.3126 | 422614.4999 | 0 | 0 | 71237.25 | 0 | 343723 | 349930 | 0 | 0 | 71237.25
23CFE000099.02.001.004 | Orig | 05200 | 2023 | 220112 | 25100 | 1610920 | 0000000 | 0000000 | 0000000 | 24910 | 24910 | 14741.1604 | 30463.6606 | 0 | 0 | 24687.99 | 0 | 24687.99 | 25224 | 0 | 0 | 24687.99
23CFE000099.02.001.004 | Orig | 00190 | 2023 | 220112 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 104956 | 104956 | 62110.527 | 128355.8395 | 22008.07 | 23446 | 55401.82 | 211014 | 55401.82 | 65128 | 3257 | 23446 | 173075 | 2024-02-01
TASK TOTAL | [9 empty] | 129866 | 475436 | 281352 | 581434 | 22008.07 | 23446 | 151327.06 | 211014 | 423812.81 | 440282 | 3257 | 23446 | 269000.24 | 2024-04-01
23CFE000099.02.001.000 - Advanced Alloy Development
SubCLIN TOTAL | [9 empty] | 384535 | 1075675 | 618761.9268 | 1314953.1733 | 51706.675 | 39116.0739 | 313897.1299 | 456996.3714 | 858868.6299 | 901652.5554 | 15689 | 100180.9544 | 585916.48
23CFE000099.02.002.001 - Oxygen Carrier Material Performance and Durability
23CFE000099.02.002.001 | Orig | 00150 | 2022 | 220620 | 25100 | 1610314 | 0000000 | 0000000 | 0280023 | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458
TASK TOTAL | [9 empty] | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458 | 2024-03-01
23CFE000099.02.002.002 - Validation and Testing
23CFE000099.02.002.002 | Orig | 00150 | 2022 | 220140 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 345570 | 204500.3126 | 422614.4999 | 0 | 0 | 71237.25 | 0 | 343723 | 349930 | 0 | 0 | 71237.25
23CFE000099.02.002.002 | Orig | 05200 | 2022 | 220112 | 25100 | 1610920 | 0000000 | 0000000 | 0000000 | 24910 | 24910 | 14741.1604 | 30463.6606 | 0 | 0 | 24687.99 | 0 | 24687.99 | 25224 | 0 | 0 | 24687.99
23CFE000099.02.002.002 | Orig | 00190 | 2023 | 220112 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 104956 | 104956 | 62110.527 | 128355.8395 | 22008.07 | 23446 | 55401.82 | 211014 | 55401.82 | 65128 | 3257 | 23446 | 173075 | 2024-02-01
TASK TOTAL | [9 empty] | 129866 | 475436 | 281352 | 581434 | 22008.07 | 23446 | 151327.06 | 211014 | 423812.81 | 440282 | 3257 | 23446 | 269000.24 | 2024-04-01
23CFE000099.02.002.003 - Sensors and Controls
23CFE000099.02.002.003 | Orig | 00150 | 2022 | 220620 | 25100 | 1610314 | 0000000 | 0000000 | 0280023 | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458
TASK TOTAL | [9 empty] | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458 | 2024-03-01
23CFE00003.02.002.000 - Advanced Combustion - CLC
SUBCLIN TOTAL | [9 empty] | 169312 | 514882 | 338248 | 657642 | 30722.13 | 33774 | 160479.06 | 231768 | 432964.81 | 476422 | 21363 | 124026 | 311916.24
23CFE000099.02.004.001 - Development of Functional Sensor Materials for Oxygen Sensing
23CFE000099.02.004.001 | B | 00150 | 2022 | 220140 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 345570 | 204500.3126 | 422614.4999 | 0 | 0 | 71237.25 | 0 | 343723 | 349930 | 0 | 0 | 71237.25
23CFE000099.02.004.001 | B | 05200 | 2023 | 220112 | 25100 | 1610920 | 0000000 | 0000000 | 0000000 | 24910 | 24910 | 14741.1604 | 30463.6606 | 0 | 0 | 24687.99 | 0 | 24687.99 | 25224 | 0 | 0 | 24687.99
23CFE000099.02.004.001 | B | 00190 | 2023 | 220112 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 104956 | 104956 | 62110.527 | 128355.8395 | 22008.07 | 23446 | 55401.82 | 211014 | 55401.82 | 65128 | 3257 | 23446 | 173075 | 2024-02-01
TASK TOTAL | [9 empty] | 129866 | 475436 | 281352 | 581434 | 22008.07 | 23446 | 151327.06 | 211014 | 423812.81 | 440282 | 3257 | 23446 | 269000.24 | 2024-04-01
23CFE000099.02.004.002 - Field Demonstration of Distributed Temperature Measurement with Optical Fiber for Fossil Energy Power Generation Applications
23CFE000099.02.004.002 | Orig | 00150 | 2022 | 220140 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 0 | 345570 | 204500.3126 | 422614.4999 | 0 | 0 | 71237.25 | 0 | 343723 | 349930 | 0 | 0 | 71237.25
23CFE000099.02.004.002 | Orig | 05200 | 2022 | 220112 | 25100 | 1610920 | 0000000 | 0000000 | 0000000 | 24910 | 24910 | 14741.1604 | 30463.6606 | 0 | 0 | 24687.99 | 0 | 24687.99 | 25224 | 0 | 0 | 24687.99
23CFE000099.02.004.002 | Orig | 00190 | 2023 | 220112 | 25100 | 1610328 | 0000000 | 0000000 | 0000000 | 104956 | 104956 | 62110.527 | 128355.8395 | 22008.07 | 23446 | 55401.82 | 211014 | 55401.82 | 65128 | 3257 | 23446 | 173075 | 2024-02-01
TASK TOTAL | [9 empty] | 129866 | 475436 | 281352 | 581434 | 22008.07 | 23446 | 151327.06 | 211014 | 423812.81 | 440282 | 3257 | 23446 | 269000.24 | 2024-04-01
23CFE000099.02.004.003 - Raman Gas Analyzer Field Testing
23CFE000099.02.004.003 | Orig | 00150 | 2022 | 220620 | 25100 | 1610314 | 0000000 | 0000000 | 0280023 | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458
TASK TOTAL | [9 empty] | 19723 | 19723 | 28448 | 38104 | 4357.03 | 5164 | 4576 | 10377 | 4576 | 18070 | 9053 | 50290 | 21458 | 2024-03-01
23CFE000099.02.004.000 - Advanced Sensors and Controls
SUBCLIN TOTAL | [9 empty] | 279455 | 970595 | 591152 | 1200972 | 48373.17 | 52056 | 307230.12 | 432405 | 852201.62 | 898634 | 15567 | 97182 | 559458.48
23CFE000099.02.000.000 - Research Support
CLIN 2 TOTAL | [9 empty] | 833302 | 2561152 | 1548161.9268 | 3173567.1733 | 130801.975 | 124946.0739 | 781606.3099 | 1121169.3714 | 2144035.0599 | 2276708.5554 | 52619 | 321388.9544 | 1457291.2
23CFE000099.03.000.000 - Transition
23CFE000099.03.000.000 | A | 05794 | 2022 | 220520 | 25100 | 1005098 | 2004040 | 0000000 | 0000000 | 653651 | 653651 | 653651 | 653651 | 217880 | 217884 | 217880 | 435771 | 217880 | 217880 | 217884 | 50000 | 653651
CLIN 3 TOTAL | [9 empty] | 653651 | 653651 | 653651 | 653651 | 217880 | 217884 | 217880 | 435771 | 217880 | 217880 | 217884 | 50000 | 653651 | 2024-02-19
32 Total | [9 empty] | 1836542 | 5503880 | 2857686.9268 | 6244734.1733 | 416820.335 | 401506.0739 | 1559749.3699 | 1834289.3714 | 4475169.8699 | 4645330.5554 | 305787 | 471016.9544 | 2775964.44
33 Figures Expressed In: Whole Dollars | [9 empty] | 34 Signature of Participant's Project Manager and Date | [5 empty] | 35 Signature of Participant's Authorized Financial Representative and Date
36 NOTES:

## Invoice Detail
NATIONAL ENERGY TECHNOLOGY LABORATORY
INVOICE/STAFFING DATA
1 Participant Name and Address |  |  | 4 Invoice No.: 0002
MY COMPANY, LLC |  |  | 5 Invoice Date: May 14, 2024
4567 Apple Lane |  |  | 6 Billing Period: April 1 - 30, 2024
Anywhere, WV 26505
2 Contract No.: 23CFE000099
3 CLIN/SubCLIN/Task/Activity No. and Title: 01.002.000 - Education and Outreach Support
[5 empty] | Current Period | [8 empty] | Cumulative
7 Name | 8 Labor Category (E N/E) or Description | 9 Status | 10 Employer | 11 Current Rate | 12 Hours Worked of Available | 13 Total Current Period Cost | 14 Total FTE Hours | 15 Labor by Site | [5 empty] | 16 Hours | 17 Prev Costs | 18 Current Cost
[8 empty] | Mgn | Pgh | Alb | Hou | AK | Offsite
160
Pines, Barbara | Program Manager (E) | FT | MCL | 110 | 8 | 880 | 0.05 | 0.05 | [5 empty] | 12 | 440 | 1320
Little, Douglas | Senior Management Analyst (E) | FT | MCL | 95 | 16 | 1520 | 0.1 | 0.1 | [5 empty] | 24 | 760 | 2280
McGuire, Steve | Junior Management Analyst (E) | FT | MCL | 75 | 24 | 1800 | 0.15 |  | 0.15 |  |  |  |  | 36 | 900 | 2700
Walker, John | Engineer/Scientist 5 (E) | FT | JFC | 70 | 80 | 5600 | 0.5 | 0.25 | 0.25 |  |  |  |  | 120 | 2800 | 8400
Hope, Nadine | Business/Engineer Anlyst 3 (E) | FT | JFC | 64 | 64 | 4096 | 0.4 | [5 empty] | 0.4 | 96 | 2048 | 6144
Ford, Wade | Data Entry Operator 3 (N/E) | FT | MCL | 22.5 | 24 | 540 | 0.15 | [5 empty] | 0.15 | 36 | 270 | 810
| 19 DIRECT LABOR SUB-TOTAL: |  |  |  | 216 | 14436 | 1.35 | 0.4 | 0.4 | 0 | 0 | 0 | 0.55 | 324 | 7218 | 21654
| 20 LABOR G&A | 1.57% |  |  |  | 226.6452
| 21 TOTAL DIRECT LABOR |  |  |  |  | 14662.6452
|  | PLAN | ACTUAL
22 (Planned/Actual Labor hours - Current) |  | 216 | 216
23 (Planned/Actual Labor hours - Cumulative) |  | 324 | 318
24 Other Direct Costs (ODCs) | 25 Description
26 Subcontracts | BRD Consulting, Inc. |  |  |  |  | 340.5 | [8 empty] | 0 | 340.5
27 Materials | Office Supplies |  |  |  |  | 780 | [8 empty] | 500 | 1280
28 Travel | Steve McGuire |  |  |  |  | 1000 | [8 empty] | 0 | 1000
29 Training | PMI, Inc. |  |  |  |  | 1500 | [8 empty] | 1000 | 2500
30 Total ODCs | [5 empty] | 3620.5 | [8 empty] | 1500 | 5120.5
31 G&A |  | 8.5% |  |  |  | 307.7425 | [8 empty] | 270 | 577.7425
32 Fee | [5 empty] | 0 | [8 empty] | 0 | 0
33 Total Cost & Fee | [5 empty] | 18364.2425 | [8 empty] | 8988 | 27352.2425

## FTE-HC Summary Report
NATIONAL ENERGY TECHNOLOGY LABORATORY
Staffing Report Summary
FTE /Headcount Data
1 Participant Name and Address: |  |  |  |  | 2 Contract No.: | 23CFE000099
CEMENT 64 , LLC
4567 Apple Lane |  |  |  |  | 3 Reporting Period: | May 1 - 31, 2024
Myra, WV 25544
11 FTE Staffing by NETL Location
4 CLIN/SubCLIN /Task/Activity | 5 Reporting Entity | 6 Program Number | 7 Project Number | 8 WFO | 9 Local Use | 10 Reporting Period Cost | Mgn | Pgh | Alb | Hou | AK | Offsite | TOTAL
0
0
0
0
0
0
0
0
0
0
0
TOTAL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 Headcount Staffing Summary
[5 empty] | MGN | 0
[5 empty] | PGH | 0
[5 empty] | ALB | 0
[5 empty] | Hou | 0
[5 empty] | AK | 0
[5 empty] | Offsite | 0
[5 empty] | TOTAL | 0

## Open Commitment Report
OPEN COMMITMENT DETAIL REPORT
FOR PERIOD ENDING: (Enter Date)
CLIN/SubCLIN/Task/Activity | AWARD FEE (Prior Period) | AWARD FEE (Current Period) | RATE ADJUSTMENT RESERVE | LABOR | SUBCONTRACT | UNIVERSITY | SUPPLIES MATERIALS EQUIPMENT | TRAVEL/ TRAINING | OTHER 1 | TOTAL OCs
23CFE000099.01.001.000 | 5000 | 13135.55 | 4800 | 428 |  |  |  |  | 150 | 23513.55
23CFE000099.01.003.000 | 1000 | 4293.79 | 1500 | 3737 | 22727.75 |  |  | 3107.4854 |  | 36366.0254
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 6000 | 17429.34 | 6300 | 4165 | 22727.75 | 0 | 0 | 3107.4854 | 150 | 59879.5754
NOTES:
1 - Severance pay for Dona